## Slide 1: North Front Range Regional Wasteshed Solid Waste Policy Council
Solid Waste Infrastructure Master Plan Update
Oct 3, 2019

## Slide 2: Today’s Agenda
Welcome and Opening Remarks
Wasteshed Background & Overview
Solid Waste Infrastructure Project Overview
  Tier-1 Infrastructure
  Tier-2 Infrastructure
  Tier-3 Infrastructure
Timeline
Closing Remarks

## Slide 3: Wasteshed Process Overview
Foundation & Direction
  Unified Coalition Goals & Objectives
Plan Development
    Infrastructure Feasibility Study
    Market and Triple Bottom Line Analysis
    Governing Agreement Development
    Solid Waste Infrastructure Master Plan
Service
Planning
Implementation
1963
2024
2014
2019

## Slide 4: Wasteshed Coalition Goals
Establish a regional materials management system
Implement programs and facilities
Develop waste diversion/reduction goals for all parties
Conduct strong, consistent public education and outreach

## Slide 5: Wasteshed Coalition
Technical Staff
Elected Officials
(Policy Advisory Committee)
Stakeholder Advisory Group
Master Plan For Solid Waste Infrastructure

## Slide 6: Larimer County Capital Investments
New Landfill
Central Transfer Station
Yard Waste Composting Facility
Construction & Demolition Debris Processing Facility
Food Waste Composting Facility
Recycling Center Improvement
$50+ million investment
No tax revenue needed
Potential to divert 40% of landfilled waste

## Slide 7: Wasteshed Process Overview
Unified Programs & Policies
  Adoption of Intergovernmental Agreement
  Local policy consideration
  Public education alignment
Logistical Framework for Infrastructure
  Funding Mechanisms & Partnerships
Infrastructure Delivery
  Facility Design & Construction
Service
Planning
Implementation
1963
2024
2014
2019

## Slide 8: Intergovernmental Agreement
Obligations of Larimer County:
  Fund, build, own, and manage new facilities
Obligations of All Parties:
  Explore code changes for solid waste diversion
  Participate in a solid waste Policy Council
  Coordinate data tracking and education
IGA does not obligate Parties to enact new policy
  Minimum standards for waste hauling expected

## Slide 9: Supportive Local Policies
Loveland green waste commitment
Fort Collins flow control ordinance for mixed construction waste

## Slide 10: Implementation
Next Steps for Wasteshed Process:
  Wellington joining expanded and formalized Policy Council
  Facility design & development
  Municipal and County policy and program exploration
  Periodic review of Tier 2 Infrastructure
  Continued coalition collaboration
    …as directed by Policy Council

## Slide 11: Update Solid Waste Infrastructure

## Slide 12: Tier-1 Infrastructure Under Development
Central Transfer Station
New County Northern Landfill
Yard Waste Organics Windrow Processing
Construction and Demolition (C&D) Processing Facility
Notes: Relist all options under consideration.

## Slide 13: New Northern Landfill
Built to Federal Subtitle D Standards
Synthetic Liner / Ground Water Monitoring / Leachate Collection / Financial Assurance / Regulatory Oversight

## Slide 14: Northern Landfill Location

## Slide 15: Primary and Alternate Haul Routes

## Slide 16: Continue... Primary and Alternate Haul Routes

## Slide 17: Protection to Homes and External Property
Internal perimeter fencing along working areas
Large border fencing along outer perimeter
Protective berms
Daily cleanup with work crews and X-TREME LITTER VACUUM
On site weather control station to monitor wind direction and speed.

## Slide 18: New Transfer Station
Design, public review process, bid preparation
Feb 2020 – April 2020 Construction design & bid process
May 2020 – November 2021 Construction
2022 Ready for operations as needed

## Slide 19: New Yard Waste Compost Operation
02/20 Class 1 Permit submittal and CDPHE review.
03/20 – 06/20 Final Design and Bid process.
09/20 – 04/21 Construction Class 1 Compost Operation
06/21 – Start Operations

## Slide 20: Construction & Demolition Facility
2019 Market Development Overview
2020 Potential Pilot Project

## Slide 21: Tier-2 Infrastructure Future Development
Material Recovery Facility (Clean)
Aerobic Composting Including Food Waste

## Slide 22: Tier- 3 Future Consideration
  Future Consideration
Energy from Waste Facility (Direct Combustion & Conversion Technology)
Refuse Derived Fuel (RDF) Processing
  Not Currently Viable
Mixed Waste Processing (Dirty MRF)
Anaerobic Digestion

## Slide 23: Facility Development Timeline
 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024
Central Transfer Station (Jan 2019 – Feb 2022) |  |  |  |  |  | 
Public Landfill (Jan 2019 – June 2023) |  |  |  |  |  | 
Yard Waste Composting Open Windrow (Nov 2019 – June 2021) |  |  |  |  |  | 
Construction and Demolition Waste Processing (Jan 2020 – Jan 2023) |  |  |  |  |  | 
Food Waste Composting Static Aerated Bin (May 2020 – Feb 2023) |  |  |  |  |  | 

## Slide 24: Closing Remarks
Thank You
&
Next Steps